## TEKTON
S.No | ITMS NO | PROJECT NAME | MANAGER | TOOL | DEV | QA | PROD | STATUS | DURATION DEV | DURATION QA | DURATION PROD
1 | 23044 | GSPPS | ILLANGOVAN | TEKTON | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2021-11-08 | 2021-12-30 | 2022-02-10
2 | 13190 | Sourcing for Quality | HARSH TAKAWALE | TEKTON | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2021-09-15 | 2021-11-15 | 2022-01-27
3 | 21575 | FOA-Line Balancing ADP Interface | VIJAY KOMMULA | TEKTON | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2021-10-06 | 2021-02-20 | 2022-02-28
4 | 11409 | Corporate Procurement and Receiving System(CPARS) | ATHI LAKSHMI AYYAPPAN | TEKTON | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2021-12-20 | 2022-01-27 | 2022-03-25
5 | 22597 | Proof of Delivery Europe(PODE) | DEBASHIS CHAKRABORTY | TEKTON | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2021-09-16 | 2022-11-19 | 2022-01-27
6 | 858 | WIPSWeb(World Wide Integrated Purchasing System) | DIETMAR MERRELL | TEKTON | COMPLETED | INPROGRESS | NOT YET START | IN PROGRESS | 2021-10-13 | 2021-12-03 | 2022-02-14
7 | 840 | GPIRS(Global Prototype Inventory Requisition and Scheduling System) | JEFFREY BROSKI | TEKTON | COMPLETED | INPROGRESS | NOT YET START | IN PROGRESS | 2022-03-01 | 2022-05-10 | 2022-07-15
8 | 761 | Vehicle Emission Attribute Tracking (VEAT) | SYLENDRA KUMAR | JENKINS | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2022-01-02 | 2022-03-10 | 2022-04-29
9 | 445 | Regulated Attribute Verification Management (RAVM) | LAXMI | JENKINS | COMPLETED | INPROGRESS | NOT YET START | IN PROGRESS | 2022-01-07 | 2022-05-24 | 2022-07-18
10 | 1090 | North American Compliance Suite (NACS) | JAMEEL JOHN | JENKINS | COMPLETED | COMPLETED | INPROGRESS | IN PROGRESS | 2022-01-25 | 2022-03-25 | 2022-05-27
11 | 2356 | Co2 and Fuel Economy Calculator (CO2FEC | SHANEESH | JENKINS | INPROGRESS | NOT YET START | NOT YET START | IN PROGRESS | 2022-04-25 | 2022-05-25 | 2022-06-25
12 | 2589 | Heavy Duty Vehicle Verify (HD Verify) | SHANEESH | JENKINS | COMPLETED | COMPLETED | INPROGRESS | IN PROGRESS | 2022-02-18 | 2022-04-30 | 2022-06-11
13 | 3214 | E-Book | SAMEER | JENKINS | COMPLETED | COMPLETED | COMPLETED | COMPLETED | 2022-12-20 | 2022-02-08 | 2022-04-30